## Hours
Member | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | Easter | 2023-04-17 | 2023-04-24 | 2023-05-01 | Total Hours | Notes
ade12 | 3 | 4 | 5 | 9 | 7 | 8 | 7 | 5 |  | 5 | 5 | 30 | 88
dub4 | 1 | 5 | 6 | 9 | 8 | 10 | 7 | 6 |  | 4 | 9 | 34 | 99
fia5 | 4 | 2 | 8 | 9 | 5 | 9 | 6 | 8 |  | 8 | 6 | 22 | 87
gwc1 | 2 | 6 | 6 | 11 | 8 | 9 | 8 | 9 |  | 7 | 9 | 37 | 112
jag89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
jco3 | 2 | 3 | 3 | 3 | 4 | 4 | 6 | 7 |  | 9 | 6 | 36 | 83
kif11 | 3 | 7 | 7 | 9 | 7 | 5 | 8 | 8 |  | 5 | 4 | 22 | 85
tam41 | 5 | 6 | 6 | 8 | 6 | 6 | 10 | 3 |  | 5 | 5 | 37 | 97
Member | 2023-01-30: Total Hours; 2023-02-06: Hours Left; 2023-02-13: Average
ade12 | 2023-01-30: 88; 2023-02-06: -8; 2023-02-13: 8
dub4 | 2023-01-30: 99; 2023-02-06: -19; 2023-02-13: 9
fia5 | 2023-01-30: 87; 2023-02-06: -7; 2023-02-13: 7.9091
gwc1 | 2023-01-30: 112; 2023-02-06: -32; 2023-02-13: 10.1818
jag89 | 2023-01-30: 0; 2023-02-06: 80; 2023-02-13: 0
joc3 | 2023-01-30: 83; 2023-02-06: -3; 2023-02-13: 7.5455
kif11 | 2023-01-30: 85; 2023-02-06: -5; 2023-02-13: 7.7273
tam41 | 2023-01-30: 97; 2023-02-06: -17; 2023-02-13: 8.8182

## Tasks
Task | Time needed | Dependencies | Worked on by | Notes
T1: UI Spec | 0 |  | tam41, ade12
T2: Test Doc | 0 |  | gwc1, kif11, ade12
T3: Design Spec | 0 |  | jco3, tam41, kiff11, gwc1
T4: Junit Tests | 0 | T5, T6, T10, T11 | Tam41, kif11
T5: Movement | 0 |  | gwc1, ade12
T6: Check/Checkmate | 0 |  | jco3, gwc1
T7: Java fx UI | 0 | T9, T1 | fia5, gwc1
T8: Saving and Loading | 0 |  | ade12, tam41
T9: UI Presentation | 0 | T1 | fia5, jco3
T10: Castling | 0 |  | jco3, gwc1
T11: En parsant | 0 |  | jco3, gwc1
T12: Pawn promotion | 0 | T5 | fia5, dub4
T13: Test Report | 0 | T2 | dub4